## Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
| Kabeza de barangay : Boat repair and rental with google maps integration |  | 2021-06-17 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Calvin John V Placio |  | 2021-07-24 |  |  | 38
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete | Calvin Placio | 2021-06-17 | 2021-06-30 | 14 |  | Not Started
1.1 | – Requirement analysis and data gathering | Complete | Calvin Placio | 2021-06-17 | 2021-06-19 | 3 |  | In Progress
1.1.1 | –– Project analysis discussion with developer | Complete | David John Tesoro | 2021-06-21 | 2021-06-21 | 1 |  | Complete
1.2 | – Research and benchmark from existing | Complete | David John Tesoro | 2021-06-22 | 2021-06-24 | 3 |  | On Hold
1.3 | – Projections of expenses | Complete | Calvin Placio | 2021-06-25 | 2021-06-25 | 1
1.4 | – talk to Stakeholders | Complete | Calvin Placio | 2021-06-26 | 2021-06-26 | 1
1.5 | – Project team meeting | Complete | Calvin Placio | 2021-06-27 | 2021-06-28 | 2
1.6 | – Project Initiation | Complete | Calvin Placio | 2021-06-29 | 2021-06-30 | 2
2 | PROJECT DEFINITION AND PLANNING | In Progress | Calvin Placio | 2021-07-01 | 2021-07-04 | 4
2.1 | – Scope & Goal Setting | Complete | Calvin Placio | 2021-07-01 | 2021-07-01 | 1
2.2 | – Define and prepare tools needed | Complete | Shewn Carl Mercado | 2021-07-02 | 2021-07-02 | 1
2.3 | – Communication Plan | Complete | John Eroh Bauyon | 2021-07-03 | 2021-07-03 | 1
2.4 | – Define threats and disadvantage | Complete | Calvin john Placio | 2021-07-04 | 2021-07-04 | 1
3 | Development and execution | Complete | Calvin john Placio | 2021-07-05 | 2021-07-18 | 14
3.1 | – Formulate the system requirements | Complete | Calvin Placio | 2021-07-05 | 2021-07-06 | 2
3.2 | – Design database and integrate the needed technology | Complete | Calvin john Placio | 2021-07-06 | 2021-07-08 | 3
3.2.1 | –– Database designing based on the business requirements | Complete | Calvin john Placio | 2021-07-06 | 2021-07-08 | 3
3.2.2 | ––define the needed to apply the Network integration | Complete | Shewn Carl Mercado | 2021-07-07 | 2021-07-08 | 2
3.3 | – Actual Coding | In Progress | Calvin john Placio | 2021-07-09 | 2021-07-16 | 8 | Im Calvin Placio I would like to collaborate with Javier on Coding
3.3.1 | –– Perform tests on the system | Not Started | Shewn Carl Mercado | 2021-07-17 | 2021-07-18 | 2 | ImJohn Eroh I want to join on the system testing
4 | Project evaluation and closeout | Not Started | Shewn Carl Mercado | 2021-07-19 | 2021-07-24 | 6
4.1 | – Revisioning of requirementsb((if needed) | Not Started | Calvin Placio | 2021-07-19 | 2021-07-21 | 3
4.2 | –Project team System evaluation | Not Started | Calvin Placio | 2021-07-22 | 2021-07-22 | 1
4.3 | – Submision of the needed documents | Not Started | Calvin john Placio | 2021-07-23 | 2021-07-23 | 1
4.4 | – Set and meet for system presentation | Not Started | Calvin Placio | 2021-07-24 | 2021-07-24 | 1